## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Cobber RPG | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Office Heros | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead | Project Start: |  | 2022-03-17
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-03-14 to 2022-05-08
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | [56 empty] | Description | time axis 2022-03-14 to 2022-05-08
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Design |  | 40% | [59 empty] | Design: This phase contains 4 subdivisions that are goign to be described below.
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | User Interface pages | Jaleta Tesgera | 50% | 2022-03-18 | 2022-03-26 | 9 | [56 empty] | This division we are going to decide what the user interface and and the background is going to look like for the common pages: login, main page, options page, result page etc.
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Determine Scope | Segni Tulu | 25% | 2022-03-20 | 2022-03-26 | 7 | [56 empty] | Determining the scope means what is our code going to cover. Due to the limited amount of time we have we can't go in and out of every part of concordia. Thus we should decide what the map is going to cover and what interior buildings are going to be coverd by our program.
| Character Design | Segni Tulu | 10% | 2022-03-19 | 2022-03-26 | 8 | [56 empty] | As the name states it character design is going to be deciding which designs of Kernel and Niblet we are planning to use. Taking them through Adobe to adjust and make the design transparent is goign to be one of the tasks.
| Overview Map | Ye Yint Win, Jaleta Tesgera | 75% | 2022-03-19 | 2022-03-26 | 8 | [56 empty] | In the overview map, we are going to decide the different maps we are going to use for the "Study Concordia" option and the main game option as well. We will go through contents such as color codes for roads and bulidings and what and how much is seen on the users desktop at once for the game.
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Detail Study |  | 4.636% | [59 empty] | Detail Study: This phase contains 11 subdivisions that are going to be described below.
| Determine Classes & Methods | Segni Tulu, Jaleta Tesgera | 10% | 2022-03-27 | 2022-04-09 | 14 | [56 empty] | In this phase we are going to discuss in detail what the main class, classes, sub classes, interface and the methods we contain in each class are going to be.
| Relate Methods in classes | Segni Tulu | 10% | 2022-03-27 | 2022-04-02 | 7 | [56 empty] | Relating the methods and their functionalities in each class is importnat for the program to excute what we need. This step incliudes detailed study, rearesrch, and inquiry of uncommon methods.
| Login Class | Jaleta Tesgera | 5% | 2022-03-27 | 2022-04-02 | [57 empty] | This login interface has to be designed as a class and the methods in the class has to be studied. We are also going to take sample user id and passwords for the logins to sucessfully work.
| Study Cord Class | Ye Yint Win | 5% | 2022-03-27 | 2022-04-02 | [57 empty] | This Study Concordia Class interface has to be designed as a class and the methods in the class has to be studied. Additionally, the scope of options presented under this class need to be linked to other interface classes.
| Q & A Class | Segni Tulu | 5% | 2022-03-27 | 2022-04-02 | [57 empty] | This Q&A interface has to be designed as a class and the methods in the class has to be studied. Additionally, wwe have to rearsrch and decide on the most prominent and relevant Q & A subjects that only relate about the locations and maps of Concordia.
| Char Choose Class | Jaleta Tesgera | 5% | 2022-03-27 | 2022-04-02 | [57 empty] | This Character Choose class has to be designed as a class and the methods in the class has to be studied. For this class we just meed effective designs and sizing the characters and adjusting to the exterior and interior sites.
| Quiz Class | Ye Yint Win | 1% | 2022-03-27 | 2022-04-09 | 14 | [56 empty] | The Quiz has to be designed as a class and the methods in the class has to be studied. This especially is the main core of the whole game, so we have to extract useful set of questions to ask, how to randomize the questions and the depth and style of our questions. Additionally, in designing the questions we also have to decide on the grading methods.
| 4 Maps | Jaleta Tesgera | 5% | 2022-03-27 | 2022-04-09 | 14 | [56 empty] | We are thinking of having a 4 maps side-by-side like a rectange 2 top, 2 bottom and 2 routes each to get out of each map.
| Character Class | Ye Yint Win | 0% | 2022-03-27 | 2022-04-09 | 14 | [56 empty] | In this stage, we going to study about the character that how it is going to look like, the characteristics of the character and diffferent things.
| Assessment Class | Ye Yint Win | 0% | 2022-03-27 | 2022-04-09 | [57 empty] | In this stage, we are giving the user a feed back on the test results. We are going to come up with a global variable that keeps the scores. Additionally, in this part comment is also given out and if outstanding achievers wish to report the score for a job that requires being familliar with the campus then it will go through.
| Move Method | Jaleta Tesgera | 5% | 2022-03-24 | 2022-04-16 | [57 empty] | In the move method phase we are going to figure it out how we move the character.
Sample phase title block | Coding |  | 3.857% | [59 empty] | After we determine and structure our classes and create or find methods that will work with our program, we are going to start coding the program.
| Interfaces | Jaleta Tesgera | 1% | 2022-04-10 | 2022-04-23 | 14 | [56 empty] | In this phase we are going to be making all the interfaces for all the classes we discussed by using the Java GUI Swing. A few examples might me the login and log off page, the maps system, the pages in between, the assesment etc.
| Overview Map & interior | Ye Yint Win, Segni Tulu | 5% | 2022-04-10 | 2022-04-16 | 7 | [56 empty] | This task is to make the overview map of the concordia as background, with a bigger JFrame, and some interior places in need in their respective interfaces.
| Routes & Blocks | Jaleta Tesgera | 5% | 2022-04-16 | 2022-04-23 | 8 | [56 empty] | In this task, on the overview maps and the interior places in prior tasks, we are putting routes and blocks, especially blocks, so that it will create a set path for the character to move.
| Transitions | Ye Yint Win | 1% | 2022-04-16 | 2022-04-23 | 8 | [56 empty] | This task is responsible for making transitions between every interfaces.
| Buttons | Jaleta Tesgera | 5% | 2022-04-16 | 2022-04-23 | [57 empty] | This task is responsible for how each buttons are going to work in the interfaces, going back and forth.
| Move Method | Segni Tulu | 5% | 2022-03-24 | 2022-04-16 | 24 | [56 empty] | In the move method phase we are going to figure it out how we move the character.
| Create Char | Segni Tulu | 5% | 2022-04-10 | 2022-04-16 | [57 empty] | This task is to use the designed characters to be able to fit in the game and move in the routes.
Sample phase title block | Testing and Commenting |  | 0% | [59 empty] | Testing and Commenting: This phase contains 3 subdivisions that are going to be described below.
| Unit Testing for methods in each class | Segni Tulu | 0% | 2022-04-24 | 2022-04-28 | 5 | [56 empty] | In this phase, we are going to create a a testing class for each class and start coding a testing for many of the method to make sure the metods are doing what are they asked to do.
| Commenting | Segni Tulu | 0% | 2022-04-24 | 2022-04-28 | 5 | [56 empty] | In this stage, we will start commenting on each of the things that we coded to make it accessible and readable code, which will help us go back and check some other time and make it easy for other people to read it.
| Final Review | Segni Tulu | 0% | 2022-04-24 | 2022-04-28 | 5 | [56 empty] | This is a stage where we verfy everthing is work as they have been told.
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on B10: Segni Tulu Jr: Study Cord Interactive Map of the campus Map
Note on B11: Segni Tulu Jr: - Niblet - Kernal
Note on B12: Segni Tulu Jr: - Exterior - Interior(Only 1)
Note on B14: Segni Tulu Jr: - Main Class - Bunch of Interfaces - Login Class - Main Page Class - Study Cord Class - 3 Subclasses - Q & A Class - Character Choose Class
Note on B21: Segni Tulu Jr: - Interior Class

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.